## Sheet1
Unique ID | User story | Story Points | Assignee | Reviewers 1 | Reviewers 2
1.1 | As a visitor I should be able to fill a contact us form | 5 | Omar Al Arousi | Hazem Tarek | Mohamed Samer
1.2 | As a visitor I should be able to create an account | 5 | Hazem Tarek | Amr Mohamed | Amr Hesham
1.3 | As an user I should be able to log in | 5 | Hazem Tarek | Amr Mohamed | Amr Hesham
1.4 | As an user I should be able to update my account | 5 | Amr Mohamed | Seif Ashraf | Hazem Tarek
1.5 | As an user I shoud be able to delete my account | 5 | Amr Mohamed | Seif Ashraf | Hazem Tarek
1.6 | As an admin I should be able to delete any account | 5 | Mohameed Hefnawy | Amr Hesham | Mohamed Samer
1.7 | As an user I should be able to view my account | 5 | Mohameed Hefnawy | Amr Hesham | Mohamed Samer
1.8 | As a user/visitor I should be able to rate events | 5 | Seif Ashraf | Omar Mohamed | Mohameed Hefnawy
1.9 | AS an admin I should be able to delete a portal library file | 5 | Seif Ashraf | Omar Mohamed | Mohameed Hefnawy
2.1 | As a user/visitor I should be able to view the rating of events | 5 | Seif Ashraf | Omar Mohamed | Mohameed Hefnawy
2.2 | As a user/visitor I should be able to create a FAQ | 5 | Mohamed Samer | Omar Al Arousi | Amr Hesham
2.3 | As a user/visitor I should be able to reply to a FAQ | 5 | Mohamed Samer | Omar Al Arousi | Amr Hesham
2.4 | As an admin I should be able to delete a FAQ | 5 | Amr Hesham | Hazem Tarek | Amr Mohamed
2.5 | As admin I should be able to edit a FAQ | 5 | Amr Hesham | Hazem Tarek | Amr Mohamed
2.6 | As an user/visitor I should be able to read FAQs | 5 | Omar Khaled | Omar Mohamed | Omar Al Arousi
2.7 | As a user I should be able to add a file to the portal library | 5 | Omar Mohamed | Seif Ashraf | Mohameed Hefnawy
2.8 | I should be able to read portal library files | 5 | Omar Mohamed | Seif Ashraf | Mohameed Hefnawy
2.9 | As an admin I should be able to delete a photo from the library | 5 | Yaseen | Omar Khaled | Fatima
3.1 | As a user I should be able to add a photo the gallery | 5 | Fatima | Omar Khaled | Seif Ashraf
3.2 | As I user/visitor I should be able to view the gallery |  | Fatima | Omar Khaled | Seif Ashraf