## Sheet1
AWGs
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | AS A NON AUTHORIZED USER :
1.1 | I can create my account using the user name and password | 5 | amr mostafa
1.2 | I can update my account like profile attributes | 8 | amr mostafa | 1.1
1.3 | I can delete my account | 5 | amr mostafa | 1.1
1.4 | I can read frequently asked quaestions FAQs | 5 | amr hesham | 1.5
1.5 | I can create a question to be added to FAQs | 5 | amr hesham
1.6 | I can read announcements and posts | 5 | hazem tarek
1.7 | I can access all subdomains to view all announcments , and link to the website | 8 | hazem trek | 1.9&1.8
1.8 | I can view the hub | 5 | omar mohamed
1.9 | I can view homepage | 5 | omar mohamed | 1.9&1.8
1.1 | I can view the description | 5 | omar mohamed
2 | AS AN AUTHORIZED USER :
2.1 | I can create an account using the user name and password | 5 | amr mostafa
2.2 | I can update my account like profile attributes | 8 | amr mostafa | 2.1
2.3 | I can delete my account | 5 | amr mostafa | 2.1
2.4 | I can delete a non autherised user account (as an admin) | 8 | amr mostafa | 2.1
2.5 | I can read frequently asked quaestions FAQs | 5 | amr hesham | 1.5
2.6 | I can delete frequently asked quaestions FAQs (as an admin) | 8 | amr hesham | 2.5
2.7 | I can respond to frequently asked quaestions FAQs | 5 | amr hesham | 2.5
2.8 | I can create announcements | 8 | hazem tarek
2.9 | I can update announcements (as an admin) | 8 | hazem tarek | 2.8
2.1 | I can read announcements and posts | 5 | hazem tarek | 2.8
2.11 | I can view hub | 5 | seif sallam
2.12 | I can view description | 5 | seif sallam | 2.11
2.13 | I can view homepage | 5 | seif sallam
2.14 | I can access all subdomains | 8 | seif sallam | 2.11
MUN Website
Unique ID | User story | Story Points | Assignee | Depends on | Testing User Story?
1 | AS A NON AUTHORIZED USER :
1.1 | I can create account using the user name and password | 5 | hazem tarek
1.2 | I can update account like profile attributes | 8 | hazem tarek | 1.1
1.3 | I can delete account | 5 | hazem tarek | 1.1
1.4 | I can read events | 5 | amr hesham
1.5 | I can rate events | 8 | amr hesham | 1.4
1.6 | I can read timeline | 5 | arrousi
1.7 | I can submit info into registration form | 8 | arrousi
2 | AS AN AUTHORIZED USER :
2.1 | I can create account using the user name and password | 5 | omar mohamed
2.2 | I can update account like profile attributes | 8 | omar mohamed | 2.1
2.3 | I can delete account | 5 | omar mohamed | 2.1
2.4 | I can delete account of a non authorized user (as an admin) | 8 | omar mohamed | 2.1
2.5 | I can read timeline | 5 | arrousi | 1.6
2.6 | I can read registration form | 5 | arrousi | 1.7
2.7 | I can update registration form | 8 | arrousi
2.8 | I can read portal library | 5 | arrousi
2.9 | I can add to portal library | 8 | arrousi | 2.8
2.1 | I can create events | 8 | arrousi
2.11 | I can read events | 5 | arrousi | 2.1
2.12 | I can update events | 8 | arrousi | 2.1